## Slide 1
Optimizing
Project Management Using Graph Theory
CS 5002 Final Project
Qiuying Zhuo & Zhiwei Zhou
2023.04

## Slide 2
CONTENT
1. Team Background
2. Graphs Theory @ Project Management
3. Questions and Hypothesis
4. Existing Theory: (CPM)
5. Case Study: Leveraging Directed Acyclic Graphs Analysis in a Promotional Event
6. Analysis: Interpretation of the Output
7. Conclusion: Reflections and Future Directions
8. References

## Slide 3
01
1. Team Background

## Slide 4
1. Team Background
Qiuying's Background:
  Investment Banker
  IPO & MA projects
  Cross-team and Cross-company Coordination
Zhiwei's Background:
  Architectural Designer
  Design Documents Phasing
  Building Permits
  Construction Administration
…
Drawings, lots of drawings…

## Slide 5
02
2. Graphs Theory @ Project Management

## Slide 6
2. Graphs Theory @ Project Management
Project Management as a common task for both of us in our previous jobs
Benefits: Make project Delivery on time, within budget, and with the desired quality
Explore the way to promote Project Management by using Discrete Math

## Slide 7
03
3. Questions and Hypothesis

## Slide 8
3. Questions and Hypothesis
1. How can Graph Theory be applied to optimize DAG-type projects, especially those time-sensitive ones, in various industries?
2. What is the earliest completion time for the project, and how can it be found?
3. Which activities can be delayed, and by how long, without affecting the minimum completion time?

## Slide 9
04
4. Existing Theory (CPM)

## Slide 10
4. Existing Theory (CPM)
Core Theory to Apply:
Critical Path Method (CPM)
Incorporating graph theory in project management
The critical path and its relation to graph theory
Finding the longest path
(the critical path)

## Slide 11
05
5. Case Study:
Leveraging Directed Acyclic Graphs Analysis in a Promotional Event

## Slide 12
5. Case Study:
Leveraging Directed Acyclic Graphs Analysis in a Promotional Event
Step 0: Construction of the promotional event scenario
Step 1: Process input data
Step 2: Represent the graph using NetworkX
Step 3: Find the critical path / the longest path
Step 4: Format and plot
Step 5: Generate summarized message

## Slide 13
06
6. Analysis: Interpretation of the Output

## Slide 14
6. Analysis: Interpretation of the Output
Output &amp; Interpretation

## Slide 15
07
7. Conclusion: Reflections and Future Directions

## Slide 16
7. Conclusion: Reflections and Future Directions
Benefits for Project Management and beyond
Things to improve
Future Development Directions

## Slide 17
08
8. References

## Slide 18
8. References
The ABCs of the Critical Path Method from Harvard Business Review
Building DAGs / Directed Acyclic Graphs with Python from MungingData
What is the "critical path" when drawing an activity-on-node network diagram that doesn't converge
Notebook 2.2- Weighted and directed graphs
HiLite.me to insert code snippet in the word document
Customizing NetworkX Graphs by Aren Carpenter

## Slide 19
THE END
THANKS
Graph Theory
is so cool ; )